## Sheet1
Name Task	Create	Finish	Max	Sign	Keterangan
Application Map	04-10-2012	04-10-2012	~	v	mari
ERD & DFD	19-04-2012		20-04
Use Case Diagram	19-04-2012		19-04
Activity Diagram	19-04-2012		19-04
Design Aplikasi
~ Form	20-04-2012	05/12	06-05-2012	v	Mari bulan mei / Lali tanggal e / :D
~ Menu	20-04-2012		06-05-2012	v
~ Button	01-05-2012		06-05-2012	v
~ Layout Plan	06-05-2012		06-05-2012	v
~ Layout All	18-06-2012		27-06-2012
Progress Develop	07-05-2012		26-06-2012
Testing Printing
Testing Client-Server
Testing Overall
Analysis Test Result
Fixing & Finalizing
Pemaketan

## Sheet2
Month Of Task	Tahun 2012
	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31
January
February
March
April
May
June
July
August
September
October
November
December

Name Task
Application Map
ERD & DFD
Use Case Diagram
Activity Diagram
Design Aplikasi	---
~ Form
~ Menu
~ Button
~ Layout Awal
~ Layout Keseluruh'an
Progress Develop
Testing Printing
Testing Client-Server
Testing Overall
Pemaketan Masa Testing
Analysis Test Result
Fixing & Finalizing
Pemaketan Fix